## Slide 1: Newberg CM report
A Review of progress for Council Goals for 2023

## Slide 2
Instead of my normal narrative report I decided to give council a run down on our smashing progress on council goals for 2023.
As you will see progress has been remarkable this year!

## Slide 3
G1 Create and maintain a high level of customer service.
CM commentary:
This bundle of objectives includes ones that can be completed in a set period of time and ones that will be ongoing in nature.
There are tangible steps that we can undertake to enhance customer service, and these are underway with step one being a published customer service standard.

## Slide 4
G1 Create and maintain a high level of customer service.
O1. Improve customer service in all departments.
Objective one is aspirational and will be an ongoing objective far into the future.
O2. Streamline the process for issuing building permits.
Objective two is under discussion with CDD staff right now and we expect the new director to tackle this as a high priority.

## Slide 5
O3. Create a team to involve engineering and planning in regular simultaneous review work.
Objective three is complete. In person meetings initiated in September of 2023 and occur weekly as a new standard part of both departments workflow.
O4. Publish a customer service standard with a measurement system.
Objective four (version 1) is complete and will be coming before council in January. Customer service manual drafting began in May of 2023. Many of the metrics are linked to delivery times for various communications channels.

## Slide 6
G2 Identify industrial land and attract employers to encourage family wage jobs.
CM commentary:
This bundle of objectives include ones that are under the city of Newberg’s control and others that will require approval of state agencies.
While I am confident that the items under our control can and will occur quickly those under state control may prove to be more challenging to enact.

## Slide 7
G2 Identify industrial land and attract employers to encourage family wage jobs.
O1. Identify land other than the Mill site to zone for Light Manufacturing.
O2. Work to bring land into the urban growth boundary to zone for light manufacturing within five years.
Initial work has been done on these items in the form of our reach to landowners adjacent to the mill site seeking interest in a future potential inclusion in the urban reserve. Thus far (December 21, 2023) four major landowners have responded positively. The mayor has directly supported the CM in this effort.

## Slide 8
G2 Identify industrial land and attract employers to encourage family wage jobs.
O3. Attract family wage jobs to Newberg using the urban renewal district and Construction Excise Tax savings to be competitive.
Complete CET was eliminated in April of 2023.
NURA and NURA CAC work is ongoing with a signed IGA and will continue decades into the future.
O4. Remove barriers/deterrents to new, “clean” / light industrial employers that will provide family wage jobs.
SDC reforms are a key component of this objective and staff hope to have a legislative package before council no later than February of 2024.

## Slide 9
G3 Ensure Newberg infrastructure (roads, water, city employees) is in good repair and supply.
CM commentary:
These objectives mostly consist of items that will never be “finished” as such. With that said great strides have been made in the efficiency of our processes including creating new job descriptions and buying new hardware. The 2022 class and compensation study and the new staff handbook are bedrock elements of the staff part of this goal.
Critically the new Neogov attract module has assisted us to becoming fully staffed in 2023!

## Slide 10
G3 Ensure Newberg infrastructure (roads, water, city employees) is in good repair and supply.
O1. Regularly review the capital improvement projects (CIPs) - annually.
Capital project review is an annual process, and it is underway for FY 24-25. The inclusion of the Open Gov budget modeling software to our new suite of apps set to occur by February 1 will accelerate these processes.
The SDC subcommittee meeting of 6/21/23 reviewed all potential CIP projects in the 30-year horizon. This provides a baseline to annual work.
The concept of shifting to two-year budget cycles needs to be discussed in the future to assist with CIPs.

## Slide 11
G3 Ensure Newberg infrastructure (roads, water, city employees) is in good repair and supply.
O2. Focus on road and sidewalk improvements in Districts 1 & 3.
The new paving drag box and sidewalk crew will answer this objective and work is ongoing on the latter. The city purchased the former early in 2023.
O3. Examine feasibility of increasing downtown parking.
Following an extensive study and review including public outreach by CDD the city plans to re-stripe and completely overhaul the municipal parking lot downtown in the summer of 2024.

## Slide 12
G4 Enhance community safety.
CM commentary:
While part of this will be ongoing for the deliverable items one is already complete and one almost complete!
Additionally, the new lightweight and responsive Emergency Operations Plan (EOP) published in November of 2023 is an overarching part of this goal.
The EOP is complete and approved!

## Slide 13
G4 Enhance community safety.
O1. Work with Newberg School District to provide an additional School Resource Officer.
Complete - Newberg School District and city staff partnered on the SRO IGAs May / June to solidify an IGA that made this a reality. SRO officer Stearns was assigned in July of 2023.
O2. Install red light and speed cameras and other speed reduction measures within two years.
Despite huge delays caused by slow ODOT review (ODOT gave permission for traffic control camera installations on 4/27/23 and 5/4/2023), the successful RFP winner Conduent was selected and the contract approved by council at the December 18th session.
We are feeling confident that we will meet the two-year deadline (February 2025 would be the two-year mark).

## Slide 14
G4 Enhance community safety.
O3. Continue with community policing partnerships.
Shop with a Cop and National Night Out were very successful this year and during the year NDPD gave presentations to all main community groups on police operations (Rotary, Kiwanis etc).
Additionally, this year our new SRO initiated classes to all Newberg School District 5th graders as part of the general anti-opioid education effort.

## Slide 15
G5 Create and maintain a high level of transparency with our residents in order to build trust.
CM commentary:
Many of these are concrete deliverables that have already been achieved or will be in the near future.
O1. Expand communication outreach in regard to regular city events and additional involvement with city businesses.
The new unified community calendar was first published in May 2023. This contains updates from the private and nonprofit sector to include the chamber of commerce and the Newberg Downtown Coalition See:
https://www.newbergoregon.gov/community/page/newberg-community-event-calendar

## Slide 16
G5 Create and maintain a high level of transparency with our residents in order to build trust.
O1. Expand communication outreach in regard to regular city events and additional involvement with city businesses, continued…
A new council powered newsletter is in the works to further assist with this goal.
The city is working on a new website to enhance this goal, contract signed in December of 2023.
Lastly the city is considering the purchase of my civic app to further this goal costs and timeline TBD. Also thank you notes in council for comments was initiated October 2023.

## Slide 17
G5 Create and maintain a high level of transparency with our residents in order to build trust.
O2. Ensure that information shared on agendas and in council meetings shall be clear and have context for the residents.
The City Recorder (CR) has worked tirelessly to create transparency in City Council Meetings and to develop simple, seamless processes that make participation in city government an easy and pleasant experience for our citizens. To date this has resulted in simplified public comment sign-ups, and new SOPs for committees.
The CR has also modified the request for council action forms to tie them into council goals, identify if state legislation is involved and provide clear executive summaries.
Built in September 2023, a unified “new in town” resources page was created: https://www.newbergoregon.gov/community/page/new-newberg

## Slide 18
G5 Create and maintain a high level of transparency with our residents in order to build trust.
O3. Legislative policy decisions shall require a work session before a vote.
Complete.
This policy was implemented as the will of council in September and October of 2023. Now all items that come before council have a separate work session always set to a preceding council meeting, unless extreme dispatch is required by the mayor and council.
In addition, the internal council packet process has been upgraded and built into our new intranet. This builds upon the reform created by the mayor in the summer of 2023 consolidating the work sessions generally to the top of the order of the business sessions.

## Slide 19
G6 Implement a careful and prudent fiscal policy.
CM commentary:
In this category we have already made great strides towards a brighter fiscal future for Newberg. I feel these objectives will all be met within a decade.

## Slide 20
G6 Implement a careful and prudent fiscal policy.
O1. Begin reducing and eventually eliminate the City’s debt in a steady, prudent way without compromising the City’s ability to provide essential services and functions.
Step one the creation of new revenue sources is underway. Many initiatives have already occurred:
The sinking fund 01-9180-800007, a contingency line of the general fund has been set up and is ready for our first year's accruals.
Funds freed up from the general fund due to the SRO partnership are available for the sinking fund.
Revenue created by the safety cameras will be available for the sinking fund (Not of course the purpose of the cameras but a useful byproduct).
A review of Newberg city owned property has been undertaken and in a prudent and careful way properties will be examined to see if they can be declared as surplus and sold (or leased) to benefit the sinking fund.

## Slide 21
G6 Implement a careful and prudent fiscal policy.
O2. Reduce elements of the municipal billing statement.
It is anticipated that the first line item will be removed as soon as the first debt is retired (the communications tower debt).
O3. The city will prudently lower System Development Charge fees.
SDC subcommittee work completed in August of 2023. The SDC reform package work initiated with legislative support from Miller Nash on 9/10/2023.

## Slide 22
G6 Implement a careful and prudent fiscal policy.
O4. Ensure that the city has a long-term financial plan that supports its goals and objectives.
It is anticipated that the Open Gov software module will be up and running by February of 2023 and this will power the creation of a long-term plan based upon securing our future water needs and debt reduction.

## Slide 23
G7 Increase land availability for housing.
CM commentary:
In this category lie some of our greatest challenges. While work is ongoing many of these sit firmly within state control and we will need to advocate for success in Salem and via the tireless work of our Community Development Division.

## Slide 24
G7 Increase land availability for housing.
O1. Seek to re-zone small pieces of land inside the city limits from light industrial to residential.
Step one is complete, a review of city owned land. A few small parcels available for housing have been identified but no work has been done yet to get construction going. If handled correctly this may raise revenue as well as provide a small amount of affordable housing.

## Slide 25
G7 Increase land availability for housing.
O2. Work to bring land into the urban growth boundary to zone for residential purposes within 5 years.
After several council presentations in 2023 including at the December 4 council session, council approved the concept of using the sequential Urban Growth Boundary (UGB) process and initiation of the Sequential UGB Process has begun. A long road stretches before us….

## Slide 26
G7 Increase land availability for housing.
O3. Look at annexation opportunities.
Always alert only the Bellair's concept has presented itself as yet.

## Slide 27: So that’s it for our review of the council goals victories of the year!
It's been hard work but very fruitful.
Questions?